# Wolfsburg Financial - Digital Transformation Strategy 2026-2028

By: Board Member Dr. Schmidt  |  Date: 2026-03-15

# Executive Summary

Wolfsburg Financial Services AG presents its digital transformation strategy for 2026-2028. The goal is complete digitalization of core processes, cloud infrastructure, and AI-powered advisory services. Total investment volume: EUR 340 million.

# Cloud Migration

85% of workloads to be cloud-based by end of 2027. Investment: EUR 120 million. Wave 1 (2026): 40% of workloads. Wave 2 (2027): 30%. Wave 3 (2028): remaining 15%. Multi-cloud approach with AWS and Azure.

# AI Transformation

Automated credit assessment (EUR 35m): processing time from 3 days to 15 minutes. AI-powered investment advisory (EUR 30m). Fraud detection (EUR 30m): neural network for real-time analysis, 60% reduction expected.

## Governance

A central transformation office oversees implementation and reports directly to the board. Key risks: IT talent shortage, legacy data migration, regulatory requirements (BaFin, EBA).